****

**Boulder County Office of Sustainability, Climate Action & Resilience**

**1325 Pearl Street, Boulder CO 80302**

**Environmental Sustainability Matching Grant Application for 2022 funding**

**PROJECT DETAILS FORM**

Please submit your application [online here](https://www.bouldercounty.org/environment/sustainability/matching-grant-program/#form) by Tuesday, Nov. 16, 2021 at 5 p.m. Before filling out the application, please read the [Grant Program Request For Funding](https://assets.bouldercounty.org/wp-content/uploads/2021/10/Sustainability-Matching-Grants_RFF-2022-funding.pdf) on the program website.

The application consists of: 1) Application Summary Form; and 2) Project Details Form. If you haven’t yet downloaded, completed, and saved the Application Summary Form, please start there. Then, download and complete a separate Project Details Form for each category you’re applying for. Attach the Project Details Form(s) to your online application before submission.

|  |  |
| --- | --- |
| **Municipality Name:**  **Town of Jamestown** | **Tax ID#: 84-1104632** |
| **Project Title: Jamestown Recycling and Zero Waste** |
| **Category of your Project: Zero Waste** |

**Project Design, Logistics and Timeline:** Please answer the following questions to describe the project you would like to implement using the requested funds. If you are requesting funding for more than one category, please complete this Project Form for EACH category and limit this form to no more than 3 pages per category.

|  |
| --- |
| 1. Scope and description of project:
* Continuation of Jamestown Recycle Saturdays consisting of 12 monthly events to be held on the second Saturday of each month. Contractor Required (GreenGirl).
* Zero Waste sponsored event. Jamestown 4th of July to be a totally Zero Waste event. Supported by contractor.
* Annual Spring Clean-up and Recycle day third Saturday in June. Supported by contractor and Boulder County Resource Conservation.
* Hard to Recycle materials- electronics, plastics, books, clothing, etc.
* Scrap metals
* Hazardous Materials- paint, batteries, automotive fluids, pesticides, mercury bulbs
* Yard waste for composting, kitchen compost
* Reuse product area.
 |
| 1. Expected Outcomes of the project:

Please include how you will measure the quantitative and qualitative success of this project, including expected outcomes, metrics, and deliverables. At the end of the calendar year and after the spring recycle/cleanup day the contractor provides weights and other measurements that we use as metrics to quantify the success during the grant period and compare to previous years. Qualitatively, we can make a judgement about how the community feels about the program because they help one another and often bring recycles from neighbors who are unable to participate in person. |
| 1. Timeline of the project:

Keep in mind that awardees are expected to complete the proposed project within a 12-month timeframe.January 8, 2022 – Recycle Saturday - $350February 12, 2022 – Recycle Saturday - $350March 12, 2022 - Recycle Saturday - $350April 9, 2022- Recycle Saturday - $350May 14, 2022 - Recycle Saturday - $350June 11, 2022 - Recycle Saturday - $350June 18, 2022 - Spring Clean-up - $960July 4, 2022 - Zero Waste Event - $1,600August 13, 2022 - Recycle Saturday - $350September 10, 2022 Recycle Saturday - $350October 8, 2022 Recycle Saturday - $350November 12, 2022 Recycle Saturday - $350December 10, 2022 Recycle Saturday - $350Total (rain or shine 10AM to noon) $6,760 |
| 1. Committed Departments, Advisory Committees, and Community Partners necessary for the success of the project:

This application is supported by the Town Board of Jamestown Resolution 09-15, 2021 (September 7, 2021)This application is supported by the Jamestown Sustainability Committee.The Jamestown Community Church has donated the use of their parking lot for Recycle Saturdays. |
| 1. What actions have already been completed to ensure the success of your project? These actions may include planning, design, coordination with departments and other stakeholders, community engagement to collect input and support, any code approvals or other city processes, etc.

We have coordinated with our recycle contractor, GreenGirl Recycling and the Clean-up Day has been scheduled with the Boulder County Resource Conservation Division (compostable yard waste) and the Hazardous Materials Management Facility.The Zero Waste event on 4th of July is coordinated with the Jamestown Volunteer Fire Department who sponsors the festival. |
| 1. Any other project details and pertinent information about why your project should be considered for Boulder County funding:

All recycle activities are open to residents of unincorporated Boulder County as well as residents of the municipality. |

**Project Budget:**

|  |  |  |
| --- | --- | --- |
| **Project Title** | **Amount of Grant Funding Requested** | **Amount of Municipal Match** |
| Jamestown Recycling and Zero Waste  | $6,760. | Volunteer Hours55.8 @ 30.31 = $1,690 |

Please contact Lea Yancey at lyancey@bouldercounty.orgwith questions.